## SPRINTS
Task ID | PRODUCT BACKLOG | Work Required | Sprint | Complete? | Sprint 1 (Mar 17 - 23) | Value 25% | Sprint 2 (Mar 24-30) | Value 25% | Sprint 3 (Mar 31 - Apr 6) | Value 25% | Sprint 4 (Apr 7 - 11) | Value 25%
1 | Work Breakdown Structure | Complete WBS, task assignment, etc. | 1 | Done | Work Breakdown Structure | Done | Edit User | Done | Create Supplier Order | Done | Presentation
2 | Use Case / User Story Glossary | Glossary of all Use Cases and actor(s) | 1 | Done | Use Case / User Story Glossary | Done | Delete User | Done | Add Supplier | Done | Weekly Status Sheet 4
3 | Login | Activity Diagram, Wireframe | 1 | Done | Login | Done | Read User | Done | Edit Supplier | Done | Team Evaluation 4
4 | Logout | N/A | N/A | Done | Add Site | Done | Create Reports | Done | Pickup Store Order | Done | Misc
5 | Move Inventory | N/A | N/A | Done | Edit Site | Done | Add Location | Done | Place Online Order | Done | Report
6 | Add Site | Wireframe | 1 | Done | View Site | Done | Create Store Order | Done | Order process | Done
7 | Edit Site | Wireframe | 1 | Done | Add User | Done | Create Emergency Order | Done | Presentation | Done
8 | View Site | Wireframe | 1 | Done | Change Password | Done | Weekly Status Sheet 2 |  | Weekly Status Sheet 3
9 | Add User | Use Case Narrative | 1 |  | Weekly Status Sheet 1 |  | Team Evaluation 2 |  | Team Evaluation 3
10 | Change Password | Sequence Diagram | 1 |  | Team Evaluation 1 |  | Misc |  | Misc
11 | Edit User | Use Case Narrative, Sequence Diagram | 2 |  | Misc |  |  |  | Report
12 | Delete User | Use Case Narrative | 2
13 | Read User | Wireframe | 2
14 | Set User Permissions | N/A | N/A
15 | Modify Record * | N/A | N/A
16 | Audit Activity | N/A | N/A
17 | Create Reports | Wireframe | 2
18 | Add Location | Wireframe | 2
19 | Create Store Order | Use Case Narrative, Wireframe | 2
20 | Create Emergency Order | Use Case Narrative, Activity Diagram | 2
21 | Accept Store Order | N/A | N/A
22 | Receive Store Order | Use Case Narrative, Wireframe | 2
23 | Prepare Store Order | N/A | N/A
24 | Fulfil Store Order | Use Case Narrative, Wireframe | 2
25 | Create Loss | N/A | N/A
26 | Process Return | N/A | N/A
27 | Add New Product | N/A | N/A
28 | Edit Product | N/A | N/A
29 | Create Supplier Order | Use Case Narrative, Wireframe, Sequence Diagram | 3
30 | Edit Inventory | N/A | N/A
31 | Add Supplier | Wireframe | 3
32 | Edit Supplier | Wireframe | 3
33 | Add Item to Backorder | N/A | N/A
34 | Edit Item | N/A | N/A
35 | Pickup Store Order | Use Case Narrative, Wireframe | 3
36 | Transport Store Order | N/A | N/A
37 | Deliver Store Order | Wireframe | 3
38 | Check Delivery | N/A | N/A
39 | Place Online Order | Activity Diagram, Wireframe | 3
40 | View Online Order | N/A | N/A
41 | Prepare Online Order | N/A | N/A
42 | Receive Online Order | N/A | N/A
43 | Order process | State Chart Diagram | 3
44 | Presentation | PowerPoint | 3
45 | Misc. | Miscellaneous Work | 1,2,3,4
46 | Weekly Status Sheet | Miscellaneous Work | 1,2,3,5
47 | Team Evaluation | Miscellaneous Work | 1,2,3,6

## Use Case Glossary
Use Case Name | Primary Actor(s) | Secondary Actor(s) | Description
Work Breakdown Structure
Use Case / User Story Glossary
Login | All |  | All employees must log in
Logout | All |  | When user logs out
Move Inventory | All |  | Used whenever inventory changes states/is added/removed
Add Site | Admin |  | Add stores, offices, warehouses ect
Edit Site | Admin |  | Display info about an existing site
View Site | Admin |  | View a list of all sites
Add User | Admin |  | Add a new user
Change Password | All |  | All employees can change the password for their account
Edit User | Admin |  | Edit info for a user
Delete User | Admin |  | Delete user
Read User | All |  | All employees can view the list and general info about other employees
Set User Permissions | Admin |  | Edit user permissions
Modify Record * | Admin |  | Modify the data of a record
Audit Activity | System |  | Create an audit record for every transaction
Create Reports | Manager, Warehouse Manager, Store Manager | Admin, System | Create a report to specifications
Add Location | Admin |  | Creation of a new database
Create Store Order | Admin | Store Manager, Asst Store Manager, Warehouse Manager | Create weekly orders for a store
Create Emergency Order | Admin | Store Manager, Asst Store Manager, Warehouse Manager | Create an emergency order for a store when required
Accept Store Order | Store Worker, Store Manager, Assistant Store Manager | Admin | Store accepts an order from driver/courier
Receive Store Order | Warehouse Manager | Admin | Manager receives order from store site
Prepare Store Order | Store Manager, Store Worker, Customer | Admin | Receive and prepare order specific to the store
Fulfil Store Order | Admin, Warehouse Manager | Warehouse Worker | Complete order for store
Create Loss | Admin | Store Manager, Warehouse Manager | Create records to track damaged or stolen goods
Process Return | Store Manager | Warehouse Manager, Admin | Create record to track returned items
Add New Product | Admin | Warehouse Manager | Add new product to inventory list
Edit Product | Admin | Warehouse Manager | Edit a product in the inventory list
Create Supplier Order | Admin | Warehouse Manager | Create supplier order
Edit Inventory | Admin | Store Manager, Warehouse Manager | Modify thresholds for reorder and optimum levels
Add Supplier | Admin, Warehouse Manager |  | Add new suppliers to the list of available suppliers
Edit Supplier | Admin, Warehouse Manager |  | Edit the information about a supplier
Add Item to Backorder | Admin, Warehouse Manager, System |  | Add ordered item to backorder
Edit Item | Admin | Warehouse Manager | Edit item information
Pickup Store Order | Driver, Warehouse Worker | Admin | Keeping track of orders
Transport Store Order | Driver | Admin | Transport order to store site
Deliver Store Order | Driver | Admin, Store Worker, Store Manager | Delivering of order to a store
Check Delivery | Admin |  | Check what orders are going out on what day of the week
Place Online Order | Customer | Admin | Placing online orders
View Online Order | Customer | Admin | Search for status of an online order
Prepare Online Order | Store Worker | Admin, Store Manager, Customer | Store receives and prepares online order
Receive Online Order | Store Worker, Customer | Admin, Store Manager | Curbside pickup when order is received at store

## Weekly Status Sheet 1
Sprint 1 (Mar 17 - 23)
Item | Task | Work Done (Details) | Team Member | Hours
1 | Misc.
2 | Weekly Status Sheet | Completed this status sheet | Nev | 0.25
3 | Team Evaluation | All team members contributed equally | Albert/Nick/Nev
4 | Work Breakdown Structure | Created WBS using Microsoft Project | Nev | 2
5 | Use Case / User Story Glossary | Completed Glossary included in this file | Nev | 2
6 | Login | Completed Wireframe and Activity Diagram | Nick/Nev | 2
7 | Add Site | Wireframe Completed to specs | Nick | 2
8 | Edit Site | Wireframe Completed to specs | Nick | 2
9 | View Site | Wireframe Completed to specs | Nick | 2
10 | Add User | Completed Use Case Diagram to specs | Albert | 2
11 | Change Password | Sequence Diagram completed to specs | Albert | 2
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Weekly Status Sheet 2
Sprint 2 (Mar 24-30)
Item | Task | Work Done (Details) | Team Member | Hours
1 | Edit User | UCN, Sequence Diagram | Albert | 1
2 | Misc.
3 | Weekly Status Sheet | To Specs | Nev | 1
4 | Team Evaluation |  | All | 1
5 | Delete User | Use Case Narrative | Albert | 1
6 | Read User | Wireframe | Nick | 1
7 | Create Reports | Wireframe | Nick | 1
8 | Add Location | Wireframe | Nick | 1
9 | Create Store Order | UCN, Wireframe | Nick, Nev | 1
10 | Create Emergency Order | UCN, Activity Diagram | Nev | 1
11 | Receive Store Order | UCN, Wireframe | Nick, Nev | 1
12 | Fulfil Store Order | UCN, Wireframe | Nick, Nev | 1
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Weekly Status Sheet 3
Sprint 3 (Mar 31 - Apr 6)
Item | Task | Work Done (Details) | Team Member | Hours
1 | Create Supplier Order | To specs | Nick, Nev | 1
2 | Misc.
3 | Weekly Status Sheet | To specs | Nev | 1
4 | Team Evaluation | To specs | All | 1
5 | Create Supplier Order
6 | Add Supplier | To specs | Nick | 1
7 | Edit Supplier | To specs | Nick | 1
8 | Pickup Store Order | To specs | Albert, Nick | 1
9 | Place Online Order | To specs | Nick, Nev | 1
10 | Order process | To specs | Albert | 1
11 | Presentation | To specs | All | 1.5
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## Weekly Status Sheet 4
Sprint 4 (Apr 7 - 11)
Item | Task | Work Done (Details) | Team Member | Hours
1 | Presentation
2 | Misc.
3 | Weekly Status Sheet
4 | Team Evaluation
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40